INTERNATIONAL CYBERSECURITY AND DIGITAL FORENSICS ACADEMY

BVWS109 – Community Development & Social Impact in Cybersecurity I

Academic Batch:   Basic Training Batch B2025

Document Type:  Project Proposal

1. PROJECT OVERVIEW & METADATA

Project Title:   Deployment of Starlink Internet Infrastructure at ICDFA Main Campus Headquarters, Lafia.

Course Code / Title:   BVWS109 – Community Development & Social Impact in Cybersecurity I (6 Credit Units).

Project Type:   Group Technology Deployment Project (Mode: One Class, One Project).

Target Community:   ICDFA Main Campus Headquarters, Lafia.

Project Supervisor:

Proposal Submission Date:

2. 	PROBLEM STATEMENT & BACKGROUND

The International Cybersecurity and Digital Forensics Academy (ICDFA) operates as a premier cybersecurity and digital forensics training institution where high-availability, high-speed internet connectivity is mission-critical. Most core academic and operational activities including online training sessions, practical cybersecurity labs, digital forensics research, cloud computing simulations, and Microsoft 365 enterprise services depend heavily on stable bandwidth.

Unstable internet connectivity directly impairs training efficiency, causes delays in practical sessions, reduces instructor productivity, and lowers the overall student experience. To establish a resilient, high-speed alternative network tier and mitigate these inefficiencies, there is an immediate need to deploy a localized, premium satellite internet infrastructure at the Main Campus Headquarters in Lafia.

3. 	PROJECT OBJECTIVES

The group project aims to design, deploy, configure, secure, test, and document a fully functional primary Starlink internet terminal. The specific technical objectives are to:

- Conduct a comprehensive localized site and structural roof assessment.

- Procure the required official Starlink hardware and specialized roof-mounting accessories.

- Safely mount the Starlink satellite dish directly onto the roof structure of the CEO's office to ensure an unobstructed line of sight.

- Route ruggedized, weatherproof cabling from the rooftop entry point down into the designated administrative workspace.

- Configure the Starlink gateway with optimized localized Wi-Fi configurations, custom SSID profiles, and a robust IP addressing scheme.

- Implement strict security hardening controls, including the restriction of administrative access and enforcement of a strong credential policy.

- Perform extensive localized connectivity testing (bandwidth, latency, jitter, and signal penetration).

- Compile and deliver a comprehensive handover documentation package to the ICDFA Technical Officer.

4. 	PROJECT SCOPE & BOUNDARIES

4.1 In-Scope

Procurement Support:   Facilitating the acquisition of the active Starlink hardware kit and designated mounting brackets.

Physical Deployment:   Handling the physical installation on the CEO's office roof, structural anchoring, and weatherproofing cable entry points.

Core Configuration:   Initializing the gateway, establishing secure localized wireless networks, and customizing internal routing layouts.

Security Engineering:   Hardening the administrative panel, changing default management passwords, and drafting the Acceptable Use Policy (AUP).

Testing & Documentation:   Executing stress tests under live lab conditions and drafting the technical handover manuals.

4.2 	Out-of-Scope

Wide-Area Campus Extension:   Laying long-distance backbone cables (Cat6/Fiber) from the CEO's office to secondary administrative zones.

External Office Distribution:   Procuring and deploying secondary network switches, enterprise trunk lines, or external wireless distribution bridges to outer academy offices. The functional terminal inside the CEO's office serves as the definitive boundary line for student deployment.

5. PROPOSED METHODOLOGY & TECHNICAL PLAN

INTERNET

│

STARLINK DISH

│

STARLINK ROUTER

│

MIKROTIK hEX S

│

MANAGED GIGABIT SWITCH

│

ACCESS POINT 1

│

Staff / Admin / Students

5.1 	Physical Infrastructure & Staging

The Starlink satellite dish will be structurally anchored directly to the concrete roof structure of the CEO's office to guarantee an unhindered view of the orbital horizon. Heavy-duty, UV-resistant PVC conduits will house the proprietary connection cable along the building exterior to guard against environmental wear. Cable pass-through holes will be sealed with premium silicone sealant to prevent structural moisture leaks.

5.2 	Power Engineering

Because the academy has deployed a dedicated, constant solar power infrastructure, the Starlink router and its inline power delivery systems will be connected directly to a designated solar inverter power terminal inside the CEO’s office. This eliminates the necessity for standalone UPS hardware while ensuring uninterrupted operation during training delivery.

5.3 	Localized Network & Security Hardening

A distinct wireless footprint will be configured utilizing advanced WPA3 encryption. The default administrative management portal credentials will be changed immediately to an enterprise-grade alphanumeric string. Local administrative management access will be isolated from standard user traffic pools to ensure zero unauthorized exposure.

6. 	PROJECT TIMELINE & MILESTONES

The implementation timeline is structured as follows:

June 9 – June 12, 2026:   Finalizing Local Site Survey, Cable Path Mapping, and Requirement Gathering.

June 14, 2026 (11:59 PM):   Official Project Proposal Submission Deadline.

June 15 – June 17, 2026:   Proposal Review and Formal Approval Window.

June 18 – June 22, 2026:   Verification of Procurement Items and Delivery Inspection.

June 23 – July 10, 2026:   Hardware Deployment, Roof Mounting, and Core Configuration.

July 11 – July 16, 2026:   Security Hardening Reviews, Firewall Audits, and Signal Stress Testing.

July 17 – July 22, 2026:   System Validation, User Policy Assembly, and Handover Guide Drafts.

July 23 – July 26, 2026:   Compilation of Final Project Report and submission

July 30, 2026:   Formal Project Presentation and Technical Defense.

7. 	PROPOSED BILL OF ENGINEERING MEASUREMENT & EVALUATION

| Item | Qty | Estimated cost (₦) |
| --- | --- | --- |
| Starlink Standard Kit | 1 | 590, 000 |
| MikroTik hEX S | 1 | 90, 000 |
| TP-Link TL-SG108E Managed Switch | 1 | 45, 000 |
| TP-Link EAP225 Access Point | 1 | 90,000 |
| Installation |  | 20, 000 |
| Miscellaneous |  | 10, 000 |
|  | Total | 845,000 |

8. 	SUGGESTED TEAM STRUCTURE

The class will organize into six dedicated operational sub-teams:

- Project Coordination Team:   Controls master schedule milestones and interface tasks.

- Site Survey & Installation Team:   Assesses mounting surfaces and handles roof masonry anchoring.

- Network Configuration Team:   Customizes wireless configurations, gateway layouts, and IP pools.

- Cybersecurity Team:   Hardens access rules, protects management access keys, and designs the local usage framework.

- Testing & Validation Team:   Monitors latency, records link degradation benchmarks, and runs data stress routines.

- Documentation Team:   Directs creation of structural drawings, site maps, configurations, and final technical reports.

9. 	EXPECTED DELIVERABLES & IMPACT

Upon project sign-off, the cohort will hand over a functional, secure, and resilient high-speed satellite network terminal. By deploying an unhindered base terminal running on clean solar power, the team creates an optimized primary gateway. This ensures that the ICDFA campus technical team can seamlessly hook into and extend high-speed connectivity across the remaining offices, enabling more robust practical cybersecurity training and academic development programs.